## Issues List - FOR Pdt Mgr Only
Issue | Category | Party | Responsible | Date | Status | Critical Path | Remarks
Universe Import Logic | Workflow | EQ |  |  | Completed
Clarify scenarios where manual changes is required during data import | Workflow | EQ |  |  | Completed
Share documents needed for upload | Workflow | EQ |  |  | Completed |  | Tearsheets
Confirm non-maker/checker approvals requires role segregation (i.e. only selected people to author and/or approve) | Workflow | EQ |  |  | Completed
Confirm whether publications are live or static | Workflow | EQ |  |  | Completed
Are there any specific instructions needed to show in RWMP - disclaimers / warning / instructions to the RM/IC | GUI / Publications | EQ |  |  | Completed
How do we handle unrated securities | Workflow | EQ | Shannon | 2023-08-05 | In Progress | Yes
Confirm DL for email distribution | Workflow | EQ | Shannon | 2023-08-05 | In Progress | Yes | Email sent to Sales Surveillance Email sent to SG Markets Meeting arranged with HK
Confirm data fields to update in Factset | Data Structure | EQ | Terrence | 2023-08-01 | Completed | Yes | PM to reply on the fields required
Can we import Peer data from Factset? | Workflow | EQ | Factset | 2023-08-05 | Completed | Yes | Yes, confirmed by Factset. PM requires us to put in Peer data fields as well.
Get GR to assist with updating APEX and Factstet | Workflow | EQ | Shannon | 2023-08-05 | Completed | No | Meeting completed with Disha. GR will update Factset. Monitor to see if errors persists
Get Factset to confirm the steps to upload MSCI Megatrends (outside of IDEACT) | Workflow | EQ | Factset | 2023-08-05 | In Progress | No | Factset confirms that this is possible. Pending their advice on the next step
Confirm with Adviscent whether they can pull Blackout list from Sharepoint | Workflow | EQ | Adviscent | 2023-08-05 | In Progress | Yes | Pending confirmation
Confirm logic for drawing the correct Research House | Workflow | EQ | Shannon | 2023-08-05 | Completed | Yes | Completed. WF01 SM Logic
Check whether the Factset-DBS/Bluematrix has issues (outside of IDEACT) | Workflow | EQ | Shannon | 2023-08-05 | Completed | No | Factset still reviewing
Check whether original country of incorporation is available in Factset (e.g. Alibaba ADR - country of incorporation is CN) (Outside of IDEACT) | Workflow | EQ | Shannon | 2023-08-05 | Completed | Yes | Factset has Country of Incorporation Country of Headquarters Country of Exchange.
Confirm name for the Filtered Monitored Universe | Worflow | EQ | EQ Advisory | 2023-08-05 | In Progress | Yes
Signoff on the DBS Guidelines for Universe Definition | Worflow | EQ | EQ Advisory | 2023-08-05 | In Progress | No
Re-validate grouping for rec. Lists. It cannot only be themes and subthemes if one of the recommendation list publications is actaully group by country | GUI / Publications | Ea |  | 2023-09-08 | Done
What is required to be exported to AVQ? We have not received a list of data field / sample file yet. Please provide asap. | GUI / Publications |  |  | 2023-09-08 | Done - file received
Please provide design template for EQ rec lists asap | GUI / Publications |  | Shannon | 13.9. | OPEN
What defines a most recent change to be listed in the recent changes table on the rec list PI? Only manual changes or also when the system automatically deletes an ISIN from the list? | GUI / Publications |  |  | 2023-09-08 | Done
Please confirm added functional requirements on GUI Publications | GUI / Publications |  |  | 2023-09-08 | Done
Please answer the questions on WF01 RM - Slide Manager | GUI / Publications |  |  | 2023-09-08 | DOne
Please check questions on WF01 SM - Product Universe | workflow |  |  | 2023-09-08 | Done
Confirm added functional requirements for Company [object] to GUI01 SM - Product Universe | GUI / Publications |  |  | 2023-09-08 | Done
Confirm email flow for maker-checker process for publications | workflow |  | Shannon | 2023-09-08
Confirm additional country data field | workflow |  |  | 2023-09-13 | Done |  | Country of Headquarter to be added and to be used for the logic Countr yof Exchange to be added on EQ level as well
Bulk document upload file - Example (what will the file look like?) | Migration |  |  | 2023-09-15 | Done |  | DBS has a file already. Question to be answered: is the upload manually done by DBS or by ADV? It will be done at the beginning of UAT - TBD
Provide Meta data labels for CIs Rec Lists | GUI / Publications |  |  | 2023-09-13 | Done
Provide Meta data labels for Publications | GUI / Publications |  |  | 2023-09-13 | Done
Check adverse news file - extract "Severe Adverse News" not whole text | Universe |  | Katja | 2023-09-13
Confirm that we have received a blackout list example file | Universe |  | Katja | 2023-09-13
Confirm that we have received PRRS import file | Universe |  | Katja | 2023-09-13
Confirm headers in the publication | GUI / Publications |  | Shannon | 2023-09-13 | Done |  | Final designs received
Confirm MSCI import logic / time limit | Interfaces |  | Shannon | 2023-09-14 | Done
How many data points shall be shown in the pie charts (first 5, and then other (to be calculated by our system)) OR shall we show all segments? | GUI / Publications |  | Shannon | 2023-09-22
Confirm color scheme / order for line charts & pie charts | GUI / Publications |  | Shannon | 2023-09-18

## Workflow List
No | Workflows | Status | Release | Remarks
1 | Product Universe Import and Maintenance | Completed | 1
2 | Recommendation List Creation and Maintenance | Completed | 1
3 | Publication Creation and Maintenance - EQ Focus & Thematic Lists | Completed | 1
4 | Publication Creation and Maintenance - Daily Focus Ideas | In Progress | 1.1
5 | Publication Creation and Maintenance - Adhoc Ideas | In Progress | 1.1
6 | Securities Monitoring Workflow | Completed | 1

## Data Fields
Required | Ideas Central Attribute | Rename | Who uses this datapoint? | Action for EQ team: Rename datapoint if required | Remarks | Source: Field Name | DBS Object | Object: Company | Object: Equity | Object: Index | Widget Name | Data Type Snapshot / Trend | Seq | Unique | Import Source | [Publication map] Equity universe | [Publication map] Equity focus list | [Publication map] Equity thematic | [Publication map] Sector perspectives | [Instrument Tab] Data Fields | r
Y | Company Name | Name |  |  |  | PROPER_NAME | Company | Y | Y |  | 01. General Information | Snapshot | 1 | 01. General Information-1 | Factset |  | X | X
Y | Country | Country |  |  |  | P_DCOUNTRY | Company | Y |  |  | 01. General Information | Snapshot | 2 | 01. General Information-2 | Factset
Y | Country of Headquarter | Country of Headquarter |  |  |  | FREF_ENTITY_COUNTRY | Company | Y |  |  | 01. General Information | Snapshot |  | 01. General Information-2 | Factset
Y | Country of Exchange | Country of Exchange |  |  |  | P_EXCOUNTRY | Equity |  | Y |  | 01. General Information | Snapshot |  | 01. General Information-2 | Factset
Y | Issuer | Issuer |  |  |  | FI_NAME(ISSR) | Equity |  | Y |  | 01. General Information | Snapshot | 2 | 01. General Information-2 | Factset
Y | BBGID/FIGI | BBGID/FIGI |  |  |  | FSYM_BLOOMBERG_ID("SECURITY") | Equity |  | Y |  | 01. General Information | Snapshot | 3 | 01. General Information-3 | Factset
Y | Region | Region |  |  |  | P_DCOUNTRY("REG") | Company | Y |  |  | 01. General Information | Snapshot | 3 | 01. General Information-3 | Factset
Y | GICS Sector | Sector |  |  | To clarify with Factset on availability | FG_GICS_SECTOR | Company | Y |  |  | 01. General Information | Snapshot | 4 | 01. General Information-4 | Factset
Y | ISIN Number | ISIN |  |  |  | P_SYMBOL("ISIN") | Equity |  | Y |  | 01. General Information | Snapshot | 4 | 01. General Information-4 | Factset | X
Y | GICS Industry Groups | Industry Group |  |  | To clarify with Factset on availability | FG_GICS_INDGRP | Company | Y |  |  | 01. General Information | Snapshot | 5 | 01. General Information-5 | Factset
Y | Ticker | Ticker |  |  |  | FSYM_BLOOMBERG_TICKER("LISTING") | Equity |  | Y |  | 01. General Information | Snapshot | 5 | 01. General Information-5 | Factset | X | X | X | X
Y | GICS Industries | Industries |  |  | To clarify with Factset on availability | FG_GICS_INDUSTRY | Company | Y |  |  | 01. General Information | Snapshot | 6 | 01. General Information-6 | Factset
Y | SEDOL | SEDOL |  |  |  | P_SYMBOL("SEDOL") | Equity |  | Y |  | 01. General Information | Snapshot | 6 | 01. General Information-6 | Factset | X |  |  |  |  | X
Y | GICS sub-Industry | Sub-Industry |  |  | To clarify with Factset on availability | FG_GICS_SUBIND | Company | Y |  |  | 01. General Information | Snapshot | 7 | 01. General Information-7 | Factset
Y | Trading CCY | Currency |  |  |  | P_CURRENCY | Equity |  | Y |  | 01. General Information | Snapshot | 7 | 01. General Information-7 | Factset | X
Y | PRR | Risk Rating |  |  |  | productRiskLevel | Equity |  | Y |  | 01. General Information | Snapshot | 8 | 01. General Information-8 | PRRS | X | X | X | X
Y | Status | Status |  |  |  |  | Company | Y | Y |  | 01. General Information | Snapshot | 8 | 01. General Information-8 | Adviscent Calc
N | Status |  |  |  | Duplicated Field |  | Equity |  | Y |  | 01. General Information | Snapshot | 9 | 01. General Information-9 | Adviscent Calc
N | Equity Description |  |  | Equals to Company Name. Use Company Field insiead | Duplicated Field |  | Equity |  | Y |  | 01. General Information | Snapshot | 10 | 01. General Information-10 | Factset (IRN) | X
Y | ESG Adverse News | ESG Adverse News |  |  | 0 = YES, ALL OTHER = NO | OVERALL_SCORE |  | Y |  |  | 01. General Information | Snapshot | 10 | 01. General Information-10 | MSCI
Y | ESG Adverse News Description |  |  |  | Show value only if ESG adverse news is true | OVERALL_SUMMARY |  | Y |  |  | 01. General Information | Snapshot | 10 | 01. General Information-10 | MSCI
Y | Covered |  |  |  | TRUE, FALSE (Checkbox) | 0 |  | Y | Y |  | 01. General Information | Snapshot | 10 | 01. General Information-10 | Adviscent Calc
Y | Blackout | Blackout |  |  | TRUE, FALSE (Checkbox) | 0 | Company | Y |  |  | 01. General Information | Snapshot | 999 | 01. General Information-999 | Blackout List
N | Industry Group |  |  |  | Duplicated Field |  | Company | Y |  |  | 01. General Information | Snapshot | 999 | 01. General Information-999 | Factset | X
N | Industry Sector |  |  |  | Duplicated Field |  | Company | Y |  |  | 01. General Information | Snapshot | 999 | 01. General Information-999 | Factset | X
Y | Name_Index | Name |  |  |  | FG_NAME_IDX |  |  |  | Y | 01. General Information | Snapshot | 1 | 01. General Information-1 | Factset
N | Dividend_index | Forward Dividend Yield |  |  | Duplicated Field |  | Index |  |  | Y | 01. General Information | Snapshot | 5 | 01. General Information-5 | Factset |  | X |  | X
Y | EPS_index_Actual | EPS |  |  |  | FG_EPS_ACT_QTR(0) or FG_EPS_ACT_ANN(0) |  |  |  | Y | 01. General Information | Snapshot | 6 | 01. General Information-6 | Factset
Y | EPS_index_YoY | EPS Y-on-Y |  |  |  | FG_EPS_1YGR(0) | Index |  |  | Y | 01. General Information | Trend | 6 | 01. General Information-6 | Factset |  | X |  | X
Y | FCF Yield_index | FCF Yield |  |  |  | FG_FCF_YIELD_LTM(0) | Index |  |  | Y | 01. General Information | Snapshot | 7 | 01. General Information-7 | Factset |  | X |  | X
Y | Last price_index | Last Done Price |  |  |  | FG_PRICE(0) | Index |  |  | Y | 01. General Information | Snapshot | 2 | 01. General Information-2 | Factset |  | X
Y | Net Debt to EBITDA_index | Net Debt to EBITDA |  |  |  | FMA_NDEBT_EBITDA | Index |  |  | Y | 01. General Information | Snapshot | 8 | 01. General Information-8 | Factset |  | X
Y | P/B_index | P/B |  |  |  | FG_PBK(0) | Index |  |  | Y | 01. General Information | Snapshot | 9 | 01. General Information-9 | Factset |  | X |  | X
Y | P/E_index | Forward P/E |  |  |  | FG_PE(0) | Index |  |  | Y | 01. General Information | Snapshot | 10 | 01. General Information-10 | Factset |  | X |  | X
Y | PX Change_index | Price Change (Last Mth) |  | Last Month Last Day - First Day Price Change | Last Month Last Day - First Day Price Change | FG_PCHG | Index |  |  | Y | 01. General Information | Snapshot | 3 | 01. General Information-3 | Factset |  | X |  |  | X
N | Rating |  |  |  | Duplicated Field |  | Equity |  | Y |  | 01. General Information | Snapshot |  | 01. General Information- | Factset | X | X | X | X | X | X
Y | Revenue_index_YTD | YTD Revenue |  |  |  | FG_SALES(0CY,0,,,,NOAUDIT) | Index |  |  | Y | 01. General Information | Snapshot | 4 | 01. General Information-4 | Factset |  | X |  | X
Y | Revenue_index_YTD | YTD Revenue |  |  |  | FG_SALES(0CY,0,,,,NOAUDIT) |  |  |  | Y | 01. General Information | Trend | 11 | 01. General Information-11 | Factset
Y | ROE_index | ROE |  |  | Add peers to benchmark automatically | FG_ROE(0) | Index |  |  | Y | 01. General Information | Snapshot | 12 | 01. General Information-12 | Factset |  | X |  | X | X | X
Y | Benchmark | Benchmark |  | Add peers to benchmark automatically | Add peers to benchmark automatically |  | Equity |  | Y |  | 02. Benchmark | Snapshot | 1 | 02. Benchmark-1 | Adviscent Calc
Y | Fitch Rating | Fitch |  |  |  | FTY_RATING_INFO(0,,,IDR_LT,TEXT) | Company | Y |  |  | 02. External Rating | Snapshot | 1 | 02. External Rating-1 | Factset
Y | Moody's Rating | Moody's |  |  |  | MDY_RATING_INFO(0,,,CF,G,TEXT) | Company | Y |  |  | 02. External Rating | Snapshot | 2 | 02. External Rating-2 | Factset
Y | S&P Rating | S&P |  |  |  | SPX_RATING_INFO(0,,,G,TEXT) | Company | Y |  |  | 02. External Rating | Snapshot | 3 | 02. External Rating-3 | Factset |  |  |  |  | X | X
Y | ESG Rating | ESG Rating |  |  |  | IVA_COMPANY_RATING | Company | Y |  |  | 02. External Rating | Snapshot | 4 | 02. External Rating-4 | MSCI | X | X | X | X
Y | Carbon Emission Score | Carbon Emission |  |  |  | MSCI_CARBN_EMISS_SCORE MSCI_CARBN_EMISS_MGMT_SCORE MSCI_CARBN_EMISS_EXP_SCORE | Company | Y |  |  | 02. External Rating | Snapshot | 5 | 02. External Rating-5 | MSCI
Y | Company Portrait | Company Portrait |  |  |  | FREF_ENTITY_BUS_DESC(EXT) | Company | Y |  |  | 03. Company Portrait | Snapshot | 1 | 03. Company Portrait-1 | Factset
Y | Investment thesis | Analyst Write Up |  |  | Qn to EQ: Park under External Rating | FDS(Z2,"IRN_MR(""EQ_INV_CASE"",-1,""EQWU"",,,,0,,1,0,0)[0]") | Company | Y | Y |  | DBS Commentary | Snapshot | 2 | 03. Company Portrait-2 | Factset (IRN) |  | X | X
N | Company Write-up |  |  |  | Duplicated Field |  | Company | Y |  |  | 03. Company Portrait | Snapshot | 999 | 03. Company Portrait-999 | Factset |  | X | X
Y | Analyst | Analyst Name |  |  |  | PENDING FACTSET | Equity |  | Y |  | 03. External Rating | Snapshot | 1 | 03. External Rating-1 | Factset (IRN)
Y | Analyst rating date | Analyst Rating date |  |  |  | PENDING FACTSET | Equity |  | Y |  | 03. External Rating | Snapshot | 2 | 03. External Rating-2 | Factset (IRN)
Y | % Analyst rating Buy/Sell/Hold | % of Analyst Hold & Buy |  |  |  | COUNT(WHERE(UPPERCASE(FE_BROKER_RATING(SNAP,EST_VALUE,0,,''))=='Buy'))+COUNT(WHERE(UPPERCASE(FE_BROKER_RATING(SNAP,EST_VALUE,0,,''))=='Overweight'))")/COUNT(FE_BROKER_RATING(SNAP,EST_VALUE,0,,") | Equity |  | Y |  | 03. External Rating | Snapshot | 3 | 03. External Rating-3 | Factset
Y | Consensus Target Px | Consenus Target Price |  |  |  | FE_ESTIMATE(PRICE_TGT,MEAN,,,NOW,,,'') | Equity |  | Y |  | 03. External Rating | Snapshot | 4 | 03. External Rating-4 | Factset
Y | % Upside | % Upside |  |  |  | FE_VALUATION(UPSIDE,MEAN,,,NOW,,,'') | Equity |  | Y |  | 03. External Rating | Snapshot | 5 | 03. External Rating-5 | Factset |  | X | X | X
Y | Target price met | Target price met |  |  |  |  | Equity |  | Y |  | 03. External Rating | Snapshot | 6 | 03. External Rating-6 | Adviscent Calc
Y | Last Done Price ($) | Last Done Price |  |  |  | P_PRICE(0,,,USD) | Equity |  | Y |  | 03. External Rating | Snapshot | 7 | 03. External Rating-7 | Factset | X | X | X | X
Y | No. Analyst rating Buy/Sell/Hold | No. of Analyst Hold & Buy |  |  |  | FE_RATING(MEAN,NOTE,0,NOW,,,'') | Equity |  | Y |  | 03. External Rating | Snapshot | 8 | 03. External Rating-8 | Factset
Y | DBSV Rating | DBSV Rating |  |  |  | FE_RATING(MEAN,NOTE,0,NOW,,,'BKRF= 469') | Equity |  | Y |  | 03. External Rating | Snapshot | 9 | 03. External Rating-9 | Factset | X
Y | DBSV Target Price ($) | DBSV Target Price ($) |  |  |  | FE_ESTIMATE(PRICE_TGT,MEAN,,,NOW,,,'BKRF= 469') | Equity |  | Y |  | 03. External Rating | Snapshot | 10 | 03. External Rating-10 | Factset | X
Y | Date of DBSV Rating | Date of DBSV Rating |  |  |  | FE_BROKER_RATING_DATE(SNAP,ESTDATEN,'MM/DD/YYYY',0,,'BKRF= 469') | Equity |  | Y |  | 03. External Rating | Snapshot | 11 | 03. External Rating-11 | Factset | X
Y | Jefferies Rating | Jefferies Rating |  |  |  | FE_RATING(MEAN,NOTE,0,NOW,,,'BKRF= 512') | Equity |  | Y |  | 03. External Rating | Snapshot | 12 | 03. External Rating-12 | Factset | X
Y | Jefferies Target Price ($) | Jefferies Target Price ($) |  |  |  | FE_ESTIMATE(PRICE_TGT,MEAN,,,NOW,,,'BKRF= 512') | Equity |  | Y |  | 03. External Rating | Snapshot | 13 | 03. External Rating-13 | Factset | X
Y | Date of Jefferies Rating | Date of Jefferies Rating |  |  |  | FE_BROKER_RATING_DATE(SNAP,ESTDATEN,'MM/DD/YYYY',0,,'BKRF= 512') | Equity |  | Y |  | 03. External Rating | Snapshot | 14 | 03. External Rating-14 | Factset | X
Y | Soc Gen Rating | Soc Gen Rating |  |  |  | FE_RATING(MEAN,NOTE,0,NOW,,,'BKRF= 40') | Equity |  | Y |  | 03. External Rating | Snapshot | 15 | 03. External Rating-15 | Factset | X
Y | Soc Gen Target Price ($) | Soc Gen Target Price ($) |  |  |  | FE_ESTIMATE(PRICE_TGT,MEAN,,,NOW,,,'BKRF= 40') | Equity |  | Y |  | 03. External Rating | Snapshot | 16 | 03. External Rating-16 | Factset | X
Y | Date of Soc Gen Rating | Date of Soc Gen Rating |  |  |  | FE_BROKER_RATING_DATE(SNAP,ESTDATEN,'MM/DD/YYYY',0,,'BKRF= 40') | Equity |  | Y |  | 03. External Rating | Snapshot | 17 | 03. External Rating-17 | Factset | X
Y | Soc Gen Research Report | Soc Gen Report |  |  |  | PENDING FACTSET |  |  | Y |  | 03. External Rating | Snapshot | 18 | 03. External Rating-18 | Factset
Y | DBSR Research Report | DBSV Report |  |  |  | PENDING FACTSET |  |  | Y |  | 03. External Rating | Snapshot | 19 | 03. External Rating-19 | Factset
Y | Jefferies Research Report | Jefferies Report |  |  |  | PENDING FACTSET |  |  | Y |  | 03. External Rating | Snapshot | 20 | 03. External Rating-20 | Factset
N | Fitch Rating |  |  |  | Duplicated Field |  | Equity |  | Y |  | 03. External Rating | Snapshot | 999 | 03. External Rating-999 | Factset
N | Investment thesis |  |  |  | Duplicated Field |  | Equity |  | Y |  | 03. External Rating | Snapshot | 999 | 03. External Rating-999 | Factset
N | Moody's Rating |  |  |  | Duplicated Field |  | Equity |  | Y |  | 03. External Rating | Snapshot | 999 | 03. External Rating-999 | Factset
N | Rating comment |  |  |  | Duplicated Field |  | Equity |  | Y |  | 03. External Rating | Snapshot | 999 | 03. External Rating-999 | Factset |  |  |  |  | X
N | Rating history |  |  |  | Not required, removed by Terrence |  | Equity |  | Y |  | 03. External Rating | Snapshot |  | 03. External Rating- | Factset
Y | Peers (Name) | Name |  |  |  | PENDING FACTSET | Company | Y | Y |  | 04. Peers widget | Snapshot | 1 | 04. Peers widget-1 | Factset
Y | Peers (Fwd P/E) | Forward P/E |  |  |  | FE_VALUATION(PE,MEAN,ANN_ROLL,+1,0,,,'') |  | Y | Y |  | 04. Peers widget | Snapshot | 2 | 04. Peers widget-2 | Factset
Y | Peers (EBITDA Margins) | Margins |  |  |  | FF_NET_MGN(ANN_R,0) |  | Y | Y |  | 04. Peers widget | Snapshot | 3 | 04. Peers widget-3 | Factset
Y | Peers (FCF yield) | FCF Yield |  |  |  | TBC |  | Y | Y |  | 04. Peers widget | Snapshot | 4 | 04. Peers widget-4 | Factset
Y | Peers (Market Cap) | Market Cap (M) |  |  |  | TBC |  | Y | Y |  | 04. Peers widget | Snapshot | 5 | 04. Peers widget-5 | Factset
Y | Peers (Forward Dividend Yield) | Forward Dividend Yield |  |  |  | PENDING FACTSET |  | Y | Y |  | 04. Peers widget |  |  |  | Factset
Y | Peers (Current Price) | Price |  |  |  | PENDING FACTSET |  | Y | Y |  | 04. Peers widget |  |  |  | Factset
Y | Peers (Upside/downside) | Upside(%) |  |  |  | FE_ESTIMATE(PRICE_TGT,MEAN,,,0,,,'') |  | Y | Y |  | 04. Peers widget | Snapshot | 5 | 04. Peers widget-5 | Factset
Y | Peers (Target Price) | Target Price |  |  |  | FE_ESTIMATE(PRICE_TGT,MEAN,,,0,,,'') |  | Y | Y |  | 04. Peers widget | Snapshot | 5 | 04. Peers widget-5 | Factset
Y | Price Change (1d) | Price Change (1D) |  |  |  | P_PRICE_CHANGE(0,-1D) | Equity |  | Y |  | 04. Summary | Snapshot | 1 | 04. Summary-1 | Factset
Y | 1M Return (%) | 1M Return |  |  |  | P_PRICE_RETURNS(2,0,-1AM) | Equity |  | Y | Y | 04. Summary | Snapshot | 2 | 04. Summary-2 | Factset |  | X |  | X
Y | 3M Return (%) | 3M Return |  |  |  | P_PRICE_RETURNS(2,0,-3AM) | Equity |  | Y | Y | 04. Summary | Snapshot | 3 | 04. Summary-3 | Factset |  | X |  | X
Y | 1Y Return (%) | 1Y Return |  |  |  | P_PRICE_RETURNS(2,0,-1AY) | Equity |  | Y | Y | 04. Summary | Snapshot | 4 | 04. Summary-4 | Factset |  | X |  | X
Y | YTD % Change | Price Change (YTD) |  |  |  | P_PRICE_RETURNS(0,0CY,0) | Equity |  | Y |  | 04. Summary | Snapshot | 5 | 04. Summary-5 | Factset |  | X | X | X
Y | RSI (14 Days) | RSI (14 Days) |  |  |  | FG_PRICE_RSI(0,,,,14) | Equity |  | Y |  | 04. Summary | Snapshot | 6 | 04. Summary-6 | Factset |  |  |  | X |  | X
Y | 52 Wk High | 52 Wk High |  |  |  | P_PRICE_HIGH_PR(0,,,,,,"PRICE","INTRA","52W") | Equity |  | Y |  | 04. Summary | Snapshot | 7 | 04. Summary-7 | Factset
Y | 52 Wk Low | 52 Wk Low |  |  |  | P_PRICE_LOW_PR(0,,,,,,"PRICE","INTRA","52W") | Equity |  | Y |  | 04. Summary | Snapshot | 8 | 04. Summary-8 | Factset
Y | Market Cap (USDm) | Market Cap (M) |  |  |  | FREF_MARKET_VALUE_COMPANY(0,,,USD,,0,,"LEGACY") | Equity |  | Y |  | 04. Summary | Snapshot | 9 | 04. Summary-9 | Factset | X | X | X | X
Y | Business Segment | Business Segment Sales Breakdown |  |  | Qn to AV: Can it be shown as a Pie Chart based on the values from Factset? | FE_SEGMENT_DATA(SALES,MEAN,BUS,+1,,Y,'') | Company | Y |  |  | 05. Segment data | Snapshot | 1 | 05. Segment data-1 | Factset
Y | Geographical segment | Geographical Sales Breakdown |  |  | Qn to AV: Can it be shown as a Pie Chart based on the values from Factset? | FE_SEGMENT_DATA(SALES,MEAN,GEO,+1,,Y,'') | Company | Y |  |  | 05. Segment data | Snapshot | 2 | 05. Segment data-2 | Factset
Y | P/E chart | P/E chart |  |  |  | FF_PE(ANN_R,0,-10FY) | Equity |  | Y |  | 05. Timeseries | Snapshot | 1 | 05. Timeseries-1 | Factset
Y | Price chart | Price chart |  |  |  | P_PRICE(0,-10Y) | Equity |  | Y |  | 05. Timeseries | Snapshot | 2 | 05. Timeseries-2 | Factset |  |  |  |  | X
Y | Total Cash | Total Cash |  |  |  | FF_CCE_TOT(ANN_R,0) | Company | Y |  |  | 06. Balance Sheet | Snapshot | 1 | 06. Balance Sheet-1 | Factset
Y | Total Debt | Total Debt |  |  |  | FF_DEBT(ANN_R,0) | Company | Y |  |  | 06. Balance Sheet | Snapshot | 2 | 06. Balance Sheet-2 | Factset
Y | Total Equity | Total Equity | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_SHLDRS_EQ(ANN_R,0) | Company | Y |  |  | 06. Balance Sheet | Snapshot | 3 | 06. Balance Sheet-3 | Factset
Y | Total Assets | Total Assets | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_ASSETS(ANN_R,0) | Company | Y |  |  | 06. Balance Sheet | Snapshot | 4 | 06. Balance Sheet-4 | Factset
Y | Short Term Debt | Short Term Debt | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_DEBT_ST(ANN_R,0) | Company | Y |  |  | 06. Balance Sheet | Snapshot | 5 | 06. Balance Sheet-5 | Factset
Y | Long Term Debt | Long Term Debt | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_DEBT_LT(ANN_R,0) | Company | Y |  |  | 06. Balance Sheet | Snapshot | 6 | 06. Balance Sheet-6 | Factset
Y | Receivable Days | Receivable Days | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | FF_RECEIV_TURN_DAYS(ANN_R,0) | Company | Y |  |  | 06. Balance Sheet | Snapshot | 7 | 06. Balance Sheet-7 | Factset
Y | Inventory Days | Inventory Days | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | FF_INVEN_DAYS(ANN_R,0) | Company | Y |  |  | 06. Balance Sheet | Snapshot | 8 | 06. Balance Sheet-8 | Factset
Y | Days Payable | Days Payable | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | FF_PAY_TURN_DAYS(ANN_R,0) | Company | Y |  |  | 06. Balance Sheet | Snapshot | 9 | 06. Balance Sheet-9 | Factset
Y | Total Cash | Total Cash | FI |  | Was removed by Terrence, reinstated as FI uses it | PENDING FACTSET | Company | Y |  |  | 06. Balance Sheet | Snapshot | 10 | 06. Balance Sheet-10 | Factset
Y | Total Debt | Total Debt | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_CASH_ONLY(ANN_R,0) | Company | Y |  |  | 06. Balance Sheet | Snapshot | 999 | 06. Balance Sheet-999 | Factset
Y | Total Equity | Total Equity |  |  |  |  | Equity |  | Y |  | 06. Used In | Snapshot | 1 | 06. Used In-1 | Adviscent Calc
Y | Total Assets | Total Assets |  |  | 3 Years Historical, Current and Next Year Estimate | FF_FREE_CF(ANN_R_FCF,0) | Company | Y |  |  | 07. Cash flow metrics | Trend | 1 | 07. Cash flow metrics-1 | Factset
Y | Short Term Debt | FCF Y-on-Y Change |  |  | 3 Years Historical, Current and Next Year Estimate | FF_FREE_CF(ANN_R_FCF,0)/FF_FREE_CF(ANN_R_FCF,-1FY) - 1 | Company | Y |  |  | 07. Cash flow metrics | Trend | 2 | 07. Cash flow metrics-2 | Factset
Y | Long Term Debt | Long Term Debt |  |  | 3 Years Historical, Current and Next Year Estimate | (FF_OPER_CF(ANN_R,0) - FF_CAPEX(ANN_R,0))/FF_SALES(ANN_R,0) | Company | Y |  |  | 07. Cash flow metrics | Trend | 3 | 07. Cash flow metrics-3 | Factset
Y | Receivable Days | Receivable Days |  |  | 3 Years Historical, Current and Next Year Estimate | FF_FCF_YLD(ANN_R_FCF,0) | Company | Y |  |  | 07. Cash flow metrics | Trend | 4 | 07. Cash flow metrics-4 | Factset |  | X | X | X
Y | Inventory Days | Inventory Days | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_OPER_CF(ANN_R,0) | Company | Y |  |  | 07. Cash flow metrics | Trend | 999 | 07. Cash flow metrics-999 | Factset
N | Days Payable |  |  |  | Duplicated Field |  | Equity |  | Y |  | 07. Valuation Data | Trend | 1 | 07. Valuation Data-1 | Factset |  | X | X | X
Y | EPS | EPS |  |  |  | FF_EPS(ANN_R,0) | Equity |  | Y |  | 07. Valuation Data | Trend | 2 | 07. Valuation Data-2 | Factset |  | X |  | X
Y | EPS YoY | EPS Y-on-Y |  |  |  | FF_EPS(ANN_R,0)/FF_EPS(ANN_R,-1FY) - 1 | Equity |  | Y |  | 07. Valuation Data | Trend | 3 | 07. Valuation Data-3 | Factset |  | X |  | X
Y | Price to Earnings (P/E) | P/E |  |  |  | FF_PE(ANN_R,0) | Equity |  | Y |  | 07. Valuation Data | Snapshot | 4 | 07. Valuation Data-4 | Factset |  | X | X | X | X
Y | 20Y Avg Price to Earnings (P/E) | P/E (20Y) |  |  |  | AVG(FF_PE(ANN_R,0,-20AY)) | Equity |  | Y |  | 07. Valuation Data | Snapshot | 5 | 07. Valuation Data-5 | Factset |  |  |  | X
Y | Price to Book (P/B) | P/B |  |  |  | FF_PBK(ANN_R,0) | Equity |  | Y |  | 07. Valuation Data | Snapshot | 6 | 07. Valuation Data-6 | Factset |  | X | X | X | X
Y | Divi (%pa) | Forward Dividend Yield |  |  |  | FE_VALUATION(DIV_YLD,MEAN,ANN_ROLL,+1,0,,,'') | Company | Y | Y | Y | 08. Financial ratio | Trend | 1 | 08. Financial ratio-1 | Factset | X
N | Dividend Yield |  |  |  | Duplicated Field |  | Company | Y | Y |  | 08. Financial ratio | Snapshot | 2 | 08. Financial ratio-2 | Factset |  | X | X | X
Y | Dividend Payout Ratio | Dividend Payout Ratio |  |  |  | FF_PAY_OUT_RATIO(ANN,0) | Company | Y |  | Y | 08. Financial ratio | Snapshot | 3 | 08. Financial ratio-3 | Factset |  | X | X | X
Y | Net Debt / Equity | Net Debt / Equity |  |  |  | FF_NET_DEBT(ANN_R,0)/FF_COM_EQ(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 4 | 08. Financial ratio-4 | Factset
Y | Net Debt / EBITDA | Net Debt / EBITDA |  |  |  | FF_NET_DEBT(ANN_R,0)/FF_EBITDA_OPER(ANN_R,0) | Company | Y |  | Y | 08. Financial ratio | Snapshot | 5 | 08. Financial ratio-5 | Factset |  | X |  | X
Y | EV/EBITDA | EV / EBITDA |  |  |  | FF_ENTRPR_VAL_EBITDA_OPER(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 6 | 08. Financial ratio-6 | Factset
Y | Price/Earnings Growth (PEG Ratio) | P/E Growth |  |  |  | FE_VALUATION(PEG,MEAN,ANN_ROLL,+1,0,,,'') | Company | Y |  |  | 08. Financial ratio | Snapshot | 7 | 08. Financial ratio-7 | Factset |  |  |  | X | X
Y | Return on Equity (%) | ROE |  |  |  | FF_ROE(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 8 | 08. Financial ratio-8 | Factset |  |  |  | X |  | X
Y | [Cash+CFO]/ST Debt | [Cash+CFO] / ST Debt | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | (FF_CASH_ST(ANN_R,0)+FF_OPER_CF(ANN_R,0))/FF_DEBT_ST(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
Y | Combined Ratio | Combined Ratio | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_LOSS_EXP_RATIO | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
N | Debt/Assets |  |  |  | Not required, removed by Terrence |  | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
N | Debt/EBITDA |  |  |  | Not required, removed by Terrence |  | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
N | Debt/Equity |  |  |  | Not required, removed by Terrence |  | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
Y | EBITDA/Int Exp | EBITDA / Int Exp | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | FF_EBITDA_OPER(ANN_R,0)/FF_INT_EXP_NET(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
Y | FCF/Total Debt | FCF / Total Debt | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_FREE_CF(ANN_R_FCF,0)/FF_DEBT(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
Y | Leverage Ratio | Leverage Ratio | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_BK_LEV_RATIO(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
N | Net Debt/Assets |  |  |  | Not required, removed by Terrence |  | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
Y | ROA | ROA | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | FF_ROA(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
Y | ST Debt/Total Debt | ST Debt / Total Debt | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | FF_DEBT_ST(ANN_R)/FF_DEBT(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
Y | Total Debt/Assets | Total Debt / Asset | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_DEBT_ASSETS(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
Y | Total Debt/EBITDA | Total Debt / EBITDA | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_DEBT(ANN_R,0)/FF_EBITDA_OPER(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
Y | Total Debt/Equity | Total Debt / Equity | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_DEBT_EQ(ANN_R,0) | Company | Y |  |  | 08. Financial ratio | Snapshot | 999 | 08. Financial ratio-999 | Factset
Y | EBITDA | EBITDA |  |  |  | FF_EBITDA_OPER_MGN(ANN_R,0) | Company | Y |  |  | 09. Income statement | Trend | 1 | 09. Income statement-1 | Factset
Y | EBITDA margin (%) | EBITDA Margin |  |  |  | FF_EBITDA_OPER_MGN(ANN_R,0) | Company | Y |  | Y | 09. Income statement | Trend | 2 | 09. Income statement-2 | Factset |  |  |  | X
Y | EBITDA y-o-y change | EBITDA Y-on-Y Change |  |  |  | FF_EBITDA_OPER_MGN(ANN_R,0)/FF_EBITDA_OPER_MGN(ANN_R,-1FY)-1 | Company | Y |  |  | 09. Income statement | Trend | 3 | 09. Income statement-3 | Factset
Y | Net Income | Net Income |  |  |  | FF_NET_INC(ANN_R,0) | Company | Y |  |  | 09. Income statement | Trend | 4 | 09. Income statement-4 | Factset
Y | Net Income % y-o-y | Net Income % Y-on-Y |  |  |  | FF_NET_INC(ANN_R,0)/FF_NET_INC(ANN_R,-1FY)-1 | Company | Y |  |  | 09. Income statement | Trend | 5 | 09. Income statement-5 | Factset
Y | Sales | Sales |  |  |  | FF_SALES(ANN_R,0) | Company | Y |  |  | 09. Income statement | Trend | 6 | 09. Income statement-6 | Factset
Y | Sales % y-o-y | Sales % Y-on-Y |  |  |  | FF_SALES_GR(ANN_R,-0) | Company | Y |  |  | 09. Income statement | Trend | 7 | 09. Income statement-7 | Factset |  |  |  |  | X | X
Y | Tax rate | Tax Rate |  |  |  | FF_TAX_RATE(ANN_R,0) | Company | Y |  |  | 09. Income statement | Snapshot | 8 | 09. Income statement-8 | Factset
Y | CAPEX | CAPEX | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | FF_CAPEX(ANN_R,0) | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset
N | CAPEX y-o-y change |  |  |  | Not required, removed by Terrence |  | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset
Y | EBIT | EBIT | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_EBIT_OPER(ANN_R,0) | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset
Y | EBIT Margin | EBIT Margin | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_EBIT_OPER_MGN(ANN_R,0) | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset
Y | EBIT yoy change (%) | EBIT Y-on-Y Change | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_EBIT_OPER(ANN_R,0)/FF_EBIT_OPER(ANN_R,-1FY)-1 | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset
Y | EBITDA margin | EBITDA margin | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | FF_EBITDA_OPER_MGN(ANN_R,0) | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset |  |  |  | X
Y | Gross Profit | Gross Profit | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | FF_GROSS_INC(ANN_R,0) | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset
N | Gross Profit % y-o-y |  |  |  | Not required, removed by Terrence |  | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset
N | Interest expense |  |  |  | Not required, removed by Terrence |  | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset
Y | Net Margin | Net Margin | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | FF_NET_MGN(ANN_R,0) | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset
N | Net Profit (Loss) y-o-y change |  |  |  | Not required, removed by Terrence |  | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset
N | Operating Income |  |  |  | Not required, removed by Terrence |  | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset
N | Pre-tax profit |  |  |  | Not required, removed by Terrence |  | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset |  |  |  |  | X
Y | Revenue | Revenue | Both EQ and FI |  | Was removed by Terrence, reinstated as FI uses it | FF_SALES(ANN_R,0) | Company | Y |  |  | 09. Income statement | Trend | 999 | 09. Income statement-999 | Factset |  | X |  | X | X | X
Y | CET1 Ratio | CET1 Ratio |  |  |  | FF_BK_COM_EQ_TIER1_RATIO(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 1 | 96. Banks-1 | Factset |  |  |  | X
Y | Tier 1 Ratio | Tier 1 Ratio |  |  |  | FF_CAP_RATIO_TIER1(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 2 | 96. Banks-2 | Factset
Y | Net Interest Income | Net Interest Income |  |  |  | FF_INT_INC_NET(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 3 | 96. Banks-3 | Factset
Y | Net Interest Margin | Net Interest Margin |  |  |  | FF_INT_MGN(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 4 | 96. Banks-4 | Factset
Y | Loan-to-deposit Ratio | Loan-to-deposit Ratio |  |  |  | FF_LOAN_DEPS(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 5 | 96. Banks-5 | Factset
Y | NPL Ratio | Non-Performing Loans Ratio |  |  |  | FF_NONPERF_LOAN_PCT(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 6 | 96. Banks-6 | Factset
Y | Cost-to-Income Ratio | Cost-to-Income Ratio | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_BK_EFF_RATIO(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 999 | 96. Banks-999 | Factset
Y | Liquidity Cover Ratio | Liquidity Cover Ratio | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_LOAN_DEPS(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 999 | 96. Banks-999 | Factset
Y | Non-Interest Expense | Non-Interest Expense | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_NON_INT_EXP(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 999 | 96. Banks-999 | Factset
Y | Non-Interest Income | Non-Interest Income | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_NON_INT_INC(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 999 | 96. Banks-999 | Factset
Y | Pre-Prov. Oper. Profit | Pre-Prov. Oper. Profit | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_PPNR(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 999 | 96. Banks-999 | Factset
Y | Pre-Prov. Oper. Profit yoy change (%) | Pre-Prov. Op Profit Y-on-Y Change | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_PPNR(ANN_R,0)/FF_PPNR(ANN_R,-1AY)-1 | Company | Y |  |  | 96. Banks | Trend | 999 | 96. Banks-999 | Factset
Y | Provisions | Provisions | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_LOAN_LOSS_PROV(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 999 | 96. Banks-999 | Factset
Y | Risk Weighted Assets | Risk Weighted Assets | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_ASSETS_RISK_WGHT(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 999 | 96. Banks-999 | Factset
Y | Total CAR | Total CAR | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_CAP_RATIO_TOT | Company | Y |  |  | 96. Banks | Trend | 999 | 96. Banks-999 | Factset
Y | Total Deposits | Total Deposits | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_DEPS(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 999 | 96. Banks-999 | Factset
Y | Total Loans | Total Loans | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_LOAN_GROSS(ANN_R,0) | Company | Y |  |  | 96. Banks | Trend | 999 | 96. Banks-999 | Factset
Y | Benefit Ratio | Benefit Ratio | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_LOSS_CLAIM_EXP(ANN_R,0)/FF_PREM_EARN(ANN_R,0) | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Claims and Losses | Claims and Losses | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_LOSS_CLAIM_EXP | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Claims Ratio | Claims Ratio | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_CLAIMS_NET_PREM(ANN_R,0) | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Dividends | Dividends | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_DPS(ANN,0) | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | EBIT/Interest Ratio | EBIT/Interest Ratio | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_EBIT_OPER(ANN_R,0)/FF_INT_EXP_NET(ANN_R,0) | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Expense Ratio | Expense Ratio | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_EXP_RATIO(ANN_R,0) | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Investment Income | Investment Income | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_INVEST_INC(ANN_R,0) | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Investment Income yoy change (%) | Investment Income Y-on-Y Change | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_INVEST_INC(ANN_R,0)/FF_INVEST_INC(ANN_R,-1FY)-1 | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Loss Ratio | Loss Ratio | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_LOSS_RATIO(ANN_R,0) | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Net Premium earned | Net Premium earned | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_PREM_EARN(ANN_R,0) | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Solvency I/II Ratio | Solvency I/II Ratio | FI |  | Was removed by Terrence, reinstated as FI uses it | https://go.factset.com/marketplace/catalog/product/factset-insurance-industry-solvency-ii-financials | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Total Insurance Reserv | Total Insurance Reserv | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_INS_RSRV(ANN_R,0) | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Underwriting and Acq | Underwriting and Acq | FI |  | Was removed by Terrence, reinstated as FI uses it | FF_UNDERWRITING_EXP(ANN_R,0,0) | Company | Y |  |  | 97. Insurance | Trend | 999 | 97. Insurance-999 | Factset
Y | Issued Equities and Bonds | Issued Equities and Bonds |  |  |  |  | Company | Y |  |  | 98. Issued Equities and Bonds | Snapshot | 1 | 98. Issued Equities and Bonds-1 | Manual
Y | Documents | Documents |  |  |  |  | Equity |  | Y |  | 99. Documents | Snapshot | 1 | 99. Documents-1 | Manual
Y | Used In | Used In |  |  |  |  | Company | Y |  |  | 99. Used In | Snapshot | 1 | 99. Used In-1 | Adviscent Calc
N | Index level past 1 month performance |  |  | Adddress in Px Change | Duplicated Field |  | Index |  |  | Y | 02. Performance | Trend | 1 |  | Factset |  | X
[5 empty] | x | x

## WF01 SM - Product Universe.
Workflow: Product Universe Creation and Maintenance
Functional Requirements
No, | Feature | Description | Confirmation | Release
1 | Covered Universe Flag | By default, covered universe logic derived equities are labeled with a covered tag. 1) Product Managers have the option to manually tag ISINs as part of the covered universe 2) Product Mangers have the option to filter between Covered and Full Universe | N | 1
2 | Document Upload | Attached Documents at ISIN Level 1) Equity Tear Sheets | N | 1
3 | Change History | Any manual changes on the ISIN Level needs to be captured and displayed in UI for manual changes history tracking 1) Option to lock the manual changes to provide overriding from daily refresh 2) Any manual changes to the data field will be logged and requires users to key in a reason | N | 1
3 | Peer Comparsion | Ability to compare Equities in Peers Widget 1) Attributes to compare: - Peers (Name), Peers (Market Cap, USD), Peers (Fwd P/E), Peers (EBITDA Margins), Peers (FCF Yield), Peers (Forward Dividend Yield), Peers (Current Price), Peers (Target Price), Upside/downside (%), 2) Peers are pulled from IRN | N | 1
4 | Import Failure Handling | 1) Inform RIDE and Product Manager if there is an import failure via email 2) if PRRS fails - set as last import value 3) if MSCI fails - set as last import value 4) if Blackout fails - set as last import value | N | 1 |  | RIDE - Build process for notifying RMs/ICs
5 | Last Update Date | During daily import, Product Manager can see the date in which the security is updated (i.e. imported into the platform) | N | 1
6 | Bulk Upload | Bulk upload documents as part of initial data migration 1) Attach Equity Tear Sheets to ISIN 2) Import research reports from Factset for all providers; on RMWP only show the report from the house view provider | N | 1 | Where do I find this in Data Fields -> Need to insert this at instrument level in Ideas Central
7 | Language Setting | Create English, Simplifed and Traditiona l Chinese template | N | 1
8 | House View Selection and Lock | Allow the selection and locking of House View Source | N | 1
9 | Insurance and bank data filtering | If GICS industry = Banks OR Isurance, then show widgets "Banks" and "Insurance", for all other sectors, do not show those 2 widgets |  | 1
Filtering Logic (as per discussion with Subhra on 18th Sept)
A. Jefferies Filtered House View (Jefferies Filtered) =
1. US & CAN
a. Country of Headquarters = US OR CAN AND
b. Equity.Market_cap >= 5000m AND
c. Equity.No. of Analyst Hold & Buy >=10 AND
d. Equity.No. of Analyst Hold & Buy / Equity.No. of Analyst >= 85%
2. JP & AUS
a. Country of Headquarters = JP OR AUS AND
b. Equity.Market_cap >= 1000m AND
c. Equity.No. of Analyst Hold & Buy >=5 AND
d. Equity.No. of Analyst Hold & Buy / Equity.No. of Analyst >= 85%
B. SocGen Filtered House View (SocGen Filtered) =
1. Country of Headquarters IN EU AND
2. Equity.Market_cap >= 5000m AND
3. Equity.No. of Analyst Hold & Buy >=5 AND
4. Equity.No. of Analyst Hold & Buy / Equity.No. of Analyst >= 85%
EU = (﻿﻿'SE','SS','NA','FP','BB','SM','GY','SW','GR','LI','SQ','LN','GA','IM','PL','EU')
C. DBSR Covered House View Universe (DBSR Covered)
1. All securities with a house view rating AND a research report from DBSR
Exceptions to lock in the research house - Manually overwritten Research provider
Drop HSBC, PRADA and SCB that is not from HK
HSBC (HK) – (DBSR)
Prada (HK) – (DBSR)
SCB (HK) - (DBSR)
Export AVQ
See email from Shannon on 08.09.2023
Factset export
Required attrributes to send to Factset twice a day (10am, 12pm (noon), 2pm, 4pm - after the Blackout list import);
- ISINs in covered universe
- PRR
PRRS import logic
PRRS is updated 7.00pm daily
If ISIN not found in PRRS import file, then PRRS = unrated
Import schedule: 5am; with overall import
MSCI import logic
MSCI is updated 5.00pm daily
If ISIN not found in MCSI import file, then MSCI rating = unrated
Import schedule: 5am, with overall import
Blackout list
Blackout list is updated adhoc daily, most updates performed in the morning and at noon
Import schedule: 10am, 12pm (noon), 2pm, 4pm
Analyst
System
Start
Manually updates ISIN information and attach Tear Sheets
Manually tag ISIN(s) to the Filtered Recommended Universe
Publish to Ideas Central Instrument Tab
Adds in Ideas Central Admin As input option for Offerings As input option for Content Management
Publish to Ideas Central Slide Manager As a filter for securities; As input option for generating slides
Import full universe from Data Providers
Creates / Updates Monitored Universe
Filter, Create and Update Recommended Universe to form Filtered Monitored Universe
Exports to Avaloq
Exports to FactSet
Company and Equity is linked with special functionality which can be edited manually.
!
Product Manager can toggle to see the full universe or covered universe
!
If Import/Export process is executed with failure, then the system send Email notification with the information. For import/export executed via SFTP manual job trigger is available; import/export executed via REST API also can be triggered manually but the process will be defined with API description.
!
Product Manager and Blackout updates after 7.00am are not exported to Avaloq systems until the next day.
!
Imports Data at 5.00am daily
Market Data : Factset
Investment Rationale : Factset
Product Risk Rating (updated 7.00pm daily) : PRRS
ESG Rating (updated 5.00om daily) : MSCI
Creation and Export to be completed by 7.00am daily
Compliance
Product Manager and Blackout updates are updated to Factset based on scheduled timings
8.00am, 10.00am. 12.00pm
!
Monitor Blackout Criteria remove invalidated securities

## GUI01 SM - Product Universe
Functional Requirements
No, | Feature | Description | Confirmation | Column1
1 | Search | Search by Company, Issuer or Ticker | N
2 | Download List | Ability to download list based on the filtered list. Data attributes based on the existing list data fields | N | FE in 1.0, strategy manager in 1.1
Filter Data Fields
Sequence | Front End Label NEW | Front End Label OLD | Technical Name | Type | Remarks
1 | Name | Company Name | PROPER_NAME | Multiple Selection
2 | ISIN | ISIN Number | P_SYMBOL("ISIN") | Multiple Selection
3 | Ticker | Ticker | FSYM_BLOOMBERG_TICKER("LISTING") | Multiple Selection
4 | Country | Country | P_DCOUNTRY | Multiple Selection
5 | Sector | GICS Sector | FG_GICS_SECTOR | Multiple Selection
6 | Industry Group | GICS Industry Groups | FG_GICS_INDGRP | Multiple Selection
7 | Industries | GICS Industries | FG_GICS_INDUSTRY | Multiple Selection
8 | Sub-Industry | GICS sub-Industry | FG_GICS_SUBIND | Range
9 | Forward Dividend Yield | Divi (%pa) | FE_VALUATION(DIV_YLD,MEAN,ANN_ROLL,+1,0,,,'') | Multiple Selection
10 | % Upside | % Upside | FE_VALUATION(UPSIDE,MEAN,,,NOW,,,'') | Range
11 | ESG Rating | ESG Rating | IVA_COMPANY_RATING | Multiple Selection
12 | Risk Rating | PRR | productRiskLevel | Multiple Selection
13 | Recommendation List | Recommendation List | #N/A | Multiple Selection
14 | Investment Theme | Investment Theme | #N/A | Multiple Selection
15 | Sub-Investment Theme | Sub-Theme | #N/A | Multiple Selection
16 | Market Cap (M) | Market Cap | FREF_MARKET_VALUE_COMPANY(0,,,USD,,0,,"LEGACY") | Range (FROM TO)
17 | House View Rating | Analyst Rating | #VALUE! | Multiple Selection
18 | Covered | Covered | 0 | Multiple Selection
19 | Blackout | Blackout | 0 | Multiple Selection
List Data Fields
Sequence | Front end label NEW | Front end label OLD | Technical Name | Remarks
1 | Issuer | Issuer | FI_NAME(ISSR)
2 | ISIN | ISIN Number | P_SYMBOL("ISIN")
3 | Ticker | Ticker | FSYM_BLOOMBERG_TICKER("LISTING")
4 | Sector | GICS Sector | FG_GICS_SECTOR
5 | Country | Country | P_DCOUNTRY
6 | Currency | Trading CCY | P_CURRENCY
7 | Market Cap (M) | Market Cap | FREF_MARKET_VALUE_COMPANY(0,,,USD,,0,,"LEGACY")
8 | Last Done Price | Last Done Price ($) | FG_PRICE(0)
9 | Target Price | Target price | FE_ESTIMATE(PRICE_TGT,MEAN,,,0,,,'') | House View Provider Target Price - based on logic
10 | % Upside | % Upside | FE_VALUATION(UPSIDE,MEAN,,,NOW,,,'')
11 | House View Rating | House View Rating | #N/A | House View Provider Rating - based on logic
12 | House View Provider | House View Provider | #N/A
13 | Forward Dividend Yield | Divi (%pa) | FE_VALUATION(DIV_YLD,MEAN,ANN_ROLL,+1,0,,,'')
14 | ESG Rating | ESG Rating | IVA_COMPANY_RATING
15 | Risk Rating | PRR | productRiskLevel
16 | Investment Theme | Investment Theme | #N/A
17 | Sub-Investment Theme | Sub-Investment Theme | #N/A
18 | Status | Status | 0
19 | Last Modified Date | Last Modified Date | #N/A
Filter Data Fields
Sequence | Front End Label | Technical Name | Type | Remarks
1 | GICS Sector | FG_GICS_SECTOR | Multiple Selection
2 | GICS Industry Groups | FG_GICS_INDGRP
3 | GICS Industries | FG_GICS_INDUSTRY
4 | GICS sub-Industry | FG_GICS_SUBIND
5 | Country | P_DCOUNTRY | Multiple Selection
6 | Region | P_DCOUNTRY("REG") | Multiple Selection | New attribute?
7 | Market Cap (M) | FE_VALUATION(DIV_YLD,MEAN,ANN_ROLL,+1,0,,,'') | Range (From - to)
8 | Status | 0 | Multiple Selection
9 | Investment Theme | #N/A
10 | Sub-Investment Theme | #N/A | Range
11 | Status | 0 | Multiple Selection
List Data Fields
Sequence | Front End Label | Technical Name | Remarks
1 | Company Name | PROPER_NAME
2 | GICS Sector | FG_GICS_SECTOR
3 | GICS Industry Groups | FG_GICS_INDGRP
4 | GICS Industries | FG_GICS_INDUSTRY
5 | GICS sub-Industry | FG_GICS_SUBIND
6 | Country | P_DCOUNTRY
7 | Market Cap (M) | FE_VALUATION(DIV_YLD,MEAN,ANN_ROLL,+1,0,,,'')
8 | Status | 0
9 | Last Modified Date | #N/A

## WF02 SM - Recommendation List
Workflow: Recommendation List Creation and Maintenance
No, | Feature | Description | Confirmation | Release
1 | Active Monitoring | Flag instruments which securities are flagged for blackout or active filtering which will only be shown in Ideas CentralAdmin but not in Ideas Central | N
2 | Language Setting | Create English, Simplifed and Traditiona l Chinese template - done by default | N
Filtering Logic
no filtering logic
Covered Universe created
Maker
System
Checker
Start
Creates Recommendation List
Saves Changes
Adds/Adapts Content Writeup,EQ pick(s), etc
Categorise Recommendation List Edits Meta data (i.e. Thematic, etc)
Changes status to “Published”
Publish to RMWP Slide Manager As a filter for securities As input option for generating slides
Changes status to “Authored” to trigger approval worker
Publish to RMWP Instrument As a filter
Adds in SM As input option for Content Mgmt
Monitor Blackout Criteria remove invalidated securities
Monitor Active Filtering Criteria remove invalidated securities

## GUI SM - Recommendation List EQ
| Grouping | Default ADV attributes plus below
Add Investment Theme
Add Sub-Themes
Region
Default columns follow publication columns
Meta data fields
Meta Data Fields - As-Is PLUS
|  |  | Sequence | Front End Label
|  |  | 1 | Investment Theme | These need to be the first 2 tags
|  |  | 2 | Sub-Theme
+ remaining ones that are applicable to the project

## WF01 RM - Instruments
Functional Requirements
No, | Feature | Description | Confirmation | Release
1 | Filtering of securities | Search field to cover the following attributes: Name, Ticker, ISIN |  | 1
Filter Data Fields
Sequence | Front End Label NEW | Front End Label OLD | Technical Name | Type | Remarks
1 | Name | Company Name | PROPER_NAME | Multiple Selection
2 | ISIN | ISIN Number | P_SYMBOL("ISIN") | Multiple Selection
3 | Ticker | Ticker | FSYM_BLOOMBERG_TICKER("LISTING") | Multiple Selection
4 | Country | Country | P_DCOUNTRY | Multiple Selection
5 | Sector | GICS Sector | FG_GICS_SECTOR | Multiple Selection
6 | Industry Group | GICS Industry Groups | FG_GICS_INDGRP | Multiple Selection
7 | Industries | GICS Industries | FG_GICS_INDUSTRY | Multiple Selection
8 | Sub-Industry | GICS sub-Industry | FG_GICS_SUBIND | Range
9 | Forward Dividend Yield | Divi (%pa) | FE_VALUATION(DIV_YLD,MEAN,ANN_ROLL,+1,0,,,'') | Multiple Selection
10 | % Upside | % Upside | FE_VALUATION(UPSIDE,MEAN,,,NOW,,,'') | Range
11 | ESG Rating | ESG Rating | IVA_COMPANY_RATING | Multiple Selection
12 | Risk Rating | PRR | productRiskLevel | Multiple Selection
13 | Recommendation List | Recommendation List | #N/A | Multiple Selection
14 | Investment Theme | Investment Theme | #N/A | Multiple Selection
15 | Sub-Investment Theme | Sub-Theme | #N/A | Multiple Selection
16 | Market Cap (M) | Market Cap | FREF_MARKET_VALUE_COMPANY(0,,,USD,,0,,"LEGACY") | Range (FROM TO)
17 | House View Rating | Analyst Rating | #VALUE! | Multiple Selection
18 | Covered | Covered | 0 | Multiple Selection
19 | Blackout | Blackout | 0 | Multiple Selection
20 | ESG Adverse News | ESG Adverse News | OVERALL_SCORE | Multiple Selection
List Data Fields
Sequence | Front end label NEW | Front end label OLD | Technical Name | Remarks
1 | Issuer | Issuer | FI_NAME(ISSR)
2 | ISIN | ISIN Number | P_SYMBOL("ISIN")
3 | Ticker | Ticker | FSYM_BLOOMBERG_TICKER("LISTING")
4 | Sector | GICS Sector | FG_GICS_SECTOR
5 | Country | Country | P_DCOUNTRY
6 | Currency | Trading CCY | P_CURRENCY
7 | Market Cap (M) | Market Cap | FREF_MARKET_VALUE_COMPANY(0,,,USD,,0,,"LEGACY")
8 | Last Done Price | Last Done Price ($) | FG_PRICE(0)
9 | Target Price | Target price | FE_ESTIMATE(PRICE_TGT,MEAN,,,0,,,'') | House View Provider Target Price - based on logic
10 | % Upside | % Upside | FE_VALUATION(UPSIDE,MEAN,,,NOW,,,'')
11 | House View Rating | House View Rating | #N/A | House View Provider Rating - based on logic
12 | House View Provider | House View Provider | #N/A
13 | Forward Dividend Yield | Divi (%pa) | FE_VALUATION(DIV_YLD,MEAN,ANN_ROLL,+1,0,,,'')
14 | ESG Rating | ESG Rating | IVA_COMPANY_RATING
15 | Risk Rating | PRR | productRiskLevel
16 | Investment Theme | Investment Theme | #N/A
17 | Sub-Investment Theme | Sub-Investment Theme | #N/A
18 | Status | Status | 0
19 | Last Modified Date | Last Modified Date | #N/A
20 | ESG Adverse News | ESG Adverse News | OVERALL_SCORE
Sequence | Front End Label NEW | Front End Label OLD | Technical Name | Remarks
1 | Name | Company Name | PROPER_NAME
2 | Ticker | Ticker | FSYM_BLOOMBERG_TICKER("LISTING")
3 | Country | Country | P_DCOUNTRY
3 | House View Rating | House View Analyst Rating | #N/A
4 | Sector | GICS sector | FG_GICS_SECTOR
5 | Industries | GICS Industries | FG_GICS_INDUSTRY
6 | Currency | Trading ccy | P_CURRENCY
7 | Market Cap (M) | Market Cap (USDm) | FREF_MARKET_VALUE_COMPANY(0,,,USD,,0,,"LEGACY")
8 | Risk Rating | PRR | productRiskLevel
9 | ESG Rating | ESG Rating | IVA_COMPANY_RATING
20 | ESG Adverse News | ESG Adverse News | OVERALL_SCORE
20 | ESG Adverse News Description | ESG Adverse News Description | OVERALL_SUMMARY
10 | Last Done Price | Last Done Price ($) | P_PRICE(0,,,USD)
11 | House View Target Price | House View Target Price | #N/A
12 | % Upside | % Upside | FE_VALUATION(UPSIDE,MEAN,,,NOW,,,'') | need to take house view target price - current price
13 | 52 Wk High | 52 Wk High | P_PRICE_HIGH_PR(0,,,,,,"PRICE","INTRA","52W")
14 | 52 Wk Low | 52 Wk Low | P_PRICE_LOW_PR(0,,,,,,"PRICE","INTRA","52W")
15 | Price Change (YTD) | YTD % Change | P_PRICE_RETURNS(0,0CY,0)
16 | EPS | EPS | FF_EPS(ANN_R,0)
17 | P/E | Price to Earnings (P/E) | FF_PE(ANN_R,0)
17 | Business Segment Sales Breakdown | Business Segment | FE_SEGMENT_DATA(SALES,MEAN,BUS,+1,,Y,'')
18 | P/B | Price to Book (P/B) | FF_PBK(ANN_R,0)
18 | Geographical Sales Breakdown | Geographical segment | FE_SEGMENT_DATA(SALES,MEAN,GEO,+1,,Y,'')
19 | Forward Dividend Yield | Divi (%pa) | FE_VALUATION(DIV_YLD,MEAN,ANN_ROLL,+1,0,,,'')
19 | P/E chart | P/E chart | FF_PE(ANN_R,0,-10FY)
20 | Price chart | Price chart | P_PRICE(0,-10Y)
21 | House View Source | House View Source | #N/A
21 | Analyst Write Up | Investment thesis | FDS(Z2,"IRN_MR(""EQ_INV_CASE"",-1,""EQWU"",,,,0,,1,0,0)[0]")
22 | House View Date | House View Date | #N/A | Date of last rating change
23 | Research report |  | #N/A

## WF03 SM - Pub - EQ Focus & Them
Workflow: Publication EQ Focus & Thematic Lists
Functional Requirements
No, | Feature | Description | Confirmation | Release
1 | Generating Email Templates | Automatically generate email to include the attached Factset subjects based on publication type 1. EQ Focus List 2. EQ Thematics List | N
2 | Language Setting | Create English, Simplifed and Traditiona l Chinese template - done by default | N
3 | Blackout list | Auto removal and reinstatment of equity depending on blackout status
Filtering Logic
no filtering logic
! Automatic removals / additions do not trigger the maker/checker email !
Recommendation List(s) created
Maker
System
Checker
Start
Creates Publication for Focus / Thematic List
Saves Changes
Adds/Adapts Content Writeup, Images, Rec. list(s), EQ pick(s), etc
Categorise Publication Edits Publication Meta data
Approved
Sends Email notification to Checker
Changes status to “Published”
Yes
No
Sends Email notification to Reviewer
Sends Approval Email (one template) with PDF to:
1. pbinvestappr@dbs.com
2. Maker (who pushed PI into Authored)
Publish to RWMP Portal PDF / HTML
Changes status to “Authored” to trigger approval
Monitor Blackout Criteria remove invalidated securities
Monitor Active Filtering Criteria* remove invalidated securities
Forwards received emails to RMs

## GUI Publications
Functional requirements
[6 empty] | Search field to cover the following attributes: |  | Name, Ticker, ISIN
Filter Data Fields
[6 empty] | Sequence | Front End Label NEW | Type | Remarks
[6 empty] | 1 | Type | Multiple Selection
[6 empty] | 2 | Language | Multiple Selection
[6 empty] | 3 | Author | Multiple Selection
[6 empty] | 4 | Investment Theme | Multiple Selection
[6 empty] | 5 | Sub-Theme | Multiple Selection
[6 empty] | 6 | Company | Multiple Selection
[6 empty] | 7 | Sector | Multiple Selection
[6 empty] | 8 | Country | Multiple Selection
[6 empty] | 9 | ISIN | Multiple Selection
[6 empty] | 10 | Status | Multiple Selection
List Data Fields
[6 empty] | Sequence | Front End Label NEW | Remarks
[6 empty] | 1 | Title
[6 empty] | 2 | Language
[6 empty] | 3 | Publication type/Content Type
[6 empty] | 4 | Authors
[6 empty] | 5 | Last Modified date
[6 empty] | 6 | Publication date
Refer to final designs for exact data fields and design to be applied.
For Focus List |  |  |  |  | Functional requirements
[6 empty] | No, | Feature | Description | Confirmation
[6 empty] | 1 | Market Wrap Indexes | First Row: S&P500, Nasdaq, Dow Jones Index, Russell 2000 Second Row: HSI, HSTECH, CSI300, STI Third Row: MSCI World, STOXX 600, TOPIX, ASX200 | N
[6 empty] | 2 | Recommendation - Recent changes limit | 1. System lists last 6 recent changes - Only manual changes to the recommendation list are captured in the recent recommendation changes (no automatically dropped out companies, e.g. when they are blacked out) | N
[6 empty] | 3 | Recommendation - Yearly Reset | Every 1.1.XX, the additions date needs to be reset to 1.1.XX; e.g. the actual addition was 2.12.2022, on 1.1.2023, the additions date is overwritten to 1.1.2023. | N
[6 empty] | 4 | Publication - Single Editor | All countries / themes need to be maintained in 1 editor. DRAWBACK - Single Recommendation List | N
[6 empty] | 5 | Recommendation - Change Reason | Each country / theme needs to include a text box to capture addition / removal comments. | N
[6 empty] | 6 | Document Refresh | Publications are static at publishing | N
for both Thematic and Focus List
Data Fields
[5 empty] | Sequence | Front End Label | Technical Name | Remarks
[5 empty] | 1 | Company Name | PROPER_NAME
[5 empty] | 2 | Country | P_DCOUNTRY
[5 empty] | 3 | Sector | FG_GICS_SECTOR | Not used
[5 empty] | 2 | Ticker | FSYM_BLOOMBERG_TICKER("LISTING")
[5 empty] | 3 | House View Rating | #N/A | Confirm that this is the header in the publication
[5 empty] | 4 | House View Provider | #N/A | Confirm that this is the header in the publication
[5 empty] | 5 | PRR | productRiskLevel
[5 empty] | 6 | House View Target Price | #N/A | Confirm that this is the header in the publication
[5 empty] | 7 | % Upside | FE_VALUATION(UPSIDE,MEAN,,,NOW,,,'') | need to take house view target price - current price
[5 empty] | 8 | YTD % Change | P_PRICE_RETURNS(0,0CY,0)
[5 empty] | 9 | Price to Earnings (P/E) | FF_PE(ANN_R,0)
[5 empty] | 10 | Divi (%pa) | FE_VALUATION(DIV_YLD,MEAN,ANN_ROLL,+1,0,,,'')
[5 empty] | 11 | FCF Yield | FG_FCF_YIELD_LTM(0)
[5 empty] | 12 | Price to Book (P/B) | FF_PBK(ANN_R,0)
[5 empty] | 13 | ESG Rating | IVA_COMPANY_RATING
[5 empty] | 14 | Company Portrait | FREF_ENTITY_BUS_DESC(EXT)
Meta Data fields
Meta Data Fields - As-Is PLUS
| Sequence | Front End Label | Technical Name | Remarks
| 1 | Investment Theme | #VALUE!
| 2 | Sub-Theme | #VALUE!
+ remaining ones that are applicable to the project

## WF06 SM - Securities Monitoring
Workflow: Securities Monitoring Workflow
Functional Requirements
no additional functional requirements
Filtering Logic
1. Blackout Filtering Logic
Remove blackout securities that are identified under Research and Client Solicitation https://go.mydbs.net/documents/43284126/47202892/Blackout.xls.xlsx/17804389-87e1-9928-91d1-766c096ce943?t=1591348983514
2. Active Filtering Monitoring for Filtering Logic
1. Remove Companies with Sell Calls - [Analyst Recommendation] is rated as Sell ,
2. Companies with no upside [Last Day Close Price] is equal or above the [Target Price], or
3. Companies with ESG Adverse Related News from MSCI
System
Monitor Blackout Criteria
Blackout Securities
Breach Criteria
Yes
No
Monitor Active Filtering Criteria
Companies with Sell Calls
Companies with no upside, OR
Companies with ESG severly rated news
Breach Criteria
Remove Securities from
Recommendation List
Yes
No

## WF01 RM - Slide Manager
Functional Requirements
| No, | Feature | Description | Confirmation | Release
| 1 | Filtering of securities | Search field to cover the following attributes: Name, Ticker, ISIN |  | 1
Filter Data Fields
| Sequence | Front End Label NEW | Front End Label OLD | Technical Name | Type | Remarks
| 1 | Name | Company Name | PROPER_NAME | Multiple Selection
| 2 | ISIN | ISIN Number | P_SYMBOL("ISIN") | Multiple Selection
| 3 | Ticker | Ticker | FSYM_BLOOMBERG_TICKER("LISTING") | Multiple Selection
| 4 | Country | Country | P_DCOUNTRY | Multiple Selection
| 5 | Sector | GICS Sector | FG_GICS_SECTOR | Multiple Selection
| 6 | Industry Group | GICS Industry Groups | FG_GICS_INDGRP | Multiple Selection
| 7 | Industries | GICS Industries | FG_GICS_INDUSTRY | Multiple Selection
| 8 | Sub-Industry | GICS sub-Industry | FG_GICS_SUBIND | Range
| 9 | Forward Dividend Yield | Divi (%pa) | FE_VALUATION(DIV_YLD,MEAN,ANN_ROLL,+1,0,,,'') | Multiple Selection
| 10 | % Upside | % Upside | FE_VALUATION(UPSIDE,MEAN,,,NOW,,,'') | Range
| 11 | ESG Rating | ESG Rating | IVA_COMPANY_RATING | Multiple Selection
| 12 | Risk Rating | PRR | productRiskLevel | Multiple Selection
| 13 | Recommendation List | Recommendation List | #N/A | Multiple Selection
| 14 | Investment Theme | Investment Theme | #N/A | Multiple Selection
| 15 | Sub-Investment Theme | Sub-Theme | #N/A | Multiple Selection
| 16 | Market Cap (M) | Market Cap | FREF_MARKET_VALUE_COMPANY(0,,,USD,,0,,"LEGACY") | Range (FROM TO)
| 17 | House View Rating | Analyst Rating | #N/A | Multiple Selection
| 18 | Covered | Covered | 0 | Multiple Selection
| 19 | Blackout | Blackout | 0 | Multiple Selection
List Data Fields
| Sequence | Front end label NEW | Front end label OLD | Technical Name | Remarks
| 1 | Issuer | Issuer | FI_NAME(ISSR)
| 2 | ISIN | ISIN Number | P_SYMBOL("ISIN")
| 3 | Ticker | Ticker | FSYM_BLOOMBERG_TICKER("LISTING")
| 4 | Sector | GICS Sector | FG_GICS_SECTOR
| 5 | Country | Country | P_DCOUNTRY
| 6 | Currency | Trading CCY | P_CURRENCY
| 7 | Market Cap (M) | Market Cap | #N/A
| 8 | Last Done Price | Last Done Price ($) | P_PRICE(0,,,USD)
| 9 | Target Price | Target price | #N/A | House View Provider Target Price - based on logic
| 10 | % Upside | % Upside | FE_VALUATION(UPSIDE,MEAN,,,NOW,,,'')
| 11 | House View Rating | House View Rating | #N/A | House View Provider Rating - based on logic
| 12 | House View Provider | House View Provider | #N/A | House View Provider Rating - based on logic
| 13 | Forward Dividend Yield | Divi (%pa) | FE_VALUATION(DIV_YLD,MEAN,ANN_ROLL,+1,0,,,'')
| 14 | ESG Rating | ESG Rating | IVA_COMPANY_RATING
| 15 | Risk Rating | PRR | productRiskLevel
| 16 | Investment Theme | Investment Theme | #N/A
| 17 | Sub-Investment Theme | Sub-Investment Theme | #N/A
| 18 | Status | Status | 0
| 19 | Last Modified Date | Last Modified Date | #N/A
Functional requirements
| Search field to cover the following attributes: |  | Name, Ticker, ISIN
Filter Data Fields
| Sequence | Front End Label NEW | Type | Remarks
| 1 | Type | Multiple Selection
| 2 | Language | Multiple Selection
| 3 | Author | Multiple Selection
| 4 | Investment Theme | Multiple Selection
| 5 | Sub-Theme | Multiple Selection
| 6 | Company | Multiple Selection
| 7 | Sector | Multiple Selection
| 8 | Country | Multiple Selection
| 9 | ISIN | Multiple Selection
| 10 | Status | Multiple Selection
List Data Fields
| Sequence | Front End Label NEW | Remarks
| 1 | Title
| 2 | Language
| 3 | Publication type/Content Type
| 4 | Authors
| 5 | Last Modified date
| 6 | Publication date
Refer to final designs for exact data fields and design to be applied.
Data Fields
| Sequence | Front End Label | Technical Name | Remarks
| 1 | Company Name | #REF!
| 2 | Ticker | #REF!
| 3 | Country | #REF!
| 4 | GICS sector | #REF!
| 5 | Last Done Price ($) | #REF!
| 6 | House View Target Price | #REF!
| 7 | % Upside | #REF! | need to take house view target price - current price
| 8 | YTD % Change | #REF!
| 9 | Price to Earnings (P/E) | #REF!
| 10 | Divi (%pa) | #REF!
| 11 | FCF Yield | #REF!
| 12 | Price to Book (P/B) | #REF!
| 13 | Market Cap (USDm) | #REF!
| 14 | PRR | #REF!
| 15 | ESG Rating | #REF!
| 16 | House View Source | #REF!
| 17 | House View Analyst Rating | #REF!
Data Fields
| Sequence | Front End Label | Technical Name | Remarks | Column1 | Column2
| 1 | Company Name | #REF!
| 2 | Ticker | #REF!
| 3 | Country | #REF!
| 3 | House View Analyst Rating | #REF! |  | to be added to rating box
| 4 | GICS sector | #REF!
| 5 | GICS Industries | #REF!
| 6 | Trading ccy | #REF!
| 7 | Market Cap (USDm) | #REF!
| 8 | PRR | #REF!
| 9 | ESG Rating | #REF!
| 10 | Last Done Price ($) | #REF!
| 11 | House View Target Price | #REF!
| 12 | % Upside | #REF! | need to take house view target price - current price
| 13 | 52 Wk High | #REF!
| 14 | 52 Wk Low | #REF!
| 15 | YTD % Change | #REF!
| 16 | EPS | #REF!
| 17 | Price to Earnings (P/E) | #REF!
| 17 | Business Segment | #REF!
| 18 | Price to Book (P/B) | #REF!
| 18 | Geographical segment | #REF!
| 19 | Divi (%pa) | #REF!
| 19 | P/E chart | #REF!
| 20 | FCF Yield | #REF!
| 20 | Price chart | #REF!
| 21 | House View Source | #REF!
| 21 | Investment thesis | #REF!
| 22 | House View Date | #REF! |  |  | this is the rating of when the rating of the equity was last changed.
| Order | Line Charts (Loop)
| 1 | DBS Red: #CC0000
| 2 | Grey: #A7A9AC
| 3 | Orange: #F79433
| 4 | Black: #000000
Bar Charts (Loop)
| 1 | DBS Red: #CC0000
| 2 | Grey: #A7A9AC
| 3 | Black: #000000
Pie Charts (Loop)
| 1 | DBS Red 100%: #CC0000
| 2 | DBS Red 90%: #D11A1A
| 3 | DBS Red 80%: #D63333
| 4 | DBS Red 70%: #DB4D4D
| 5 | DBS Red 60%: #E06666
| 6 | DBS Red 50%: #E68080
| 7 | DBS Red 40%: #EB9999
| 8 | DBS Red 30%: #F0B2B2
| 9 | DBS Red 20%: #F5CCCC
| 10 | Grey: #A7A9AC
| 11 | Black: #000000

## Publication - Name
No | Publication | Status | Disclaimer Used | Remarks
1 | Equity Focus List | In Progress | 03 Desk Commentaries - Specific Products; 03a Desk Commentaries - Front Page Disclaimer
2 | Equit Sector Perspectives | In Progress | 03 Desk Commentaries - Specific Products; 03a Desk Commentaries - Front Page Disclaimer

## Nomenclature description
OBJECT
Data Point
WIDGET
Data Point
Snapshot
Trend